## Sheet1
Product Backlog
Sprint | User Type | Story | Complexity | Story Points to Complete
1 | Students | As a student, I can view staff profile so that I can view contact details and background information. | 1 | 1
1 | Students | As a student, I can view student experience stories | 3 | 3
1 | Students | As a student, I can contact staff members for further information related to the course or module. | 3 | 3
1 | User | As a user, I can view the course information | 3 | 3
1 | User | As a user, I can view specific module information | 5 | 5
1 | Staff | As a staff, I can login to my staff account. | 5 | 5
1 | Non technical User (Admin) | As a non technical user (admin), I can amend staff details | 5 | 5
1 | Staff | As a staff, I can access staff portal so that I can view or manage my course/module information | 7 | 7
1 | Staff | As a staff, I can request to add or amend course information | 7 | 7
1 | Non technical User (Admin) | As a non technical user (admin), I can search for staff members | 9 | 9
1 | Non technical User (Admin) | As a non technical user (admin), I can search for course or module | 9 | 9
2 | Non technical User (Admin) | As a non technical user (admin), I can accept or reject staff requests | 1 | 1
2 | Non technical User (Admin) | As a non-technical user (admin), I can edit social media contents. | 3 | 3
2 | Non technical User (Admin) | As a non technical user (admin), I can amend the details of the course | 3 | 3
2 | Students | As a student, I can access links to computing social media | 3 | 3
2 | Staff | As a staff, I can be assigned to assist in tutoring a fellow staff member. | 7 | 7
2 | User | As a user I can access and fully use the website despite being visually impaired or having hearing disabilities. | 9 | 9
2 | Students | As a student, I can be directed to www.dundee.ac.uk to apply for the course. | 9 | 9
Total |  |  | 92 | 92