## Sheet1
Sprint 1 Backlog
Sprint | User Type | Story | Status | Complexity | Story Points Completed
1 | Students | As a student, I can view staff profile so that I can view contact details and background information. | Completed | 1 | 1
1 | Students | As a student, I can view student experience stories | Completed | 3 | 3
1 | Students | As a student, I can contact staff members for further information related to the course or module. | Completed | 3 | 3
1 | User | As a user, I can view the course information | Completed | 3 | 3
1 | User | As a user, I can view specific module information | Completed | 5 | 5
1 | Staff | As a staff, I can login to my staff account. | Completed | 5 | 5
1 | Non technical User (Admin) | As an non technical user (admin), I can amend staff details | Completed | 5 | 5
1 | Staff | As a staff, I can access staff portal so that I can view or manage my course/module information | Completed | 7 | 7
1 | Staff | As a staff, I can request to add or amend course information | Completed | 7 | 7
1 | Non technical User (Admin) | As an non technical user (admin), I can search for staff members | Completed | 9 | 9
1 | Non technical User (Admin) | As an non technical user (admin), I can search for course or module | Completed | 9 | 9
Total |  |  |  | 57 | 57
Days | Remaining story points
Monday | 57
Tuesday | 42
Wednesday | 28
Thursday | 10
Friday | 0